## Лист1
PCS development schedule
Task | Duration(w/days) | Begin | End
Projecting |  |  | April 17
Basic UI app with framework | 20 | April 17
Main media playback | 20
Secondary media | 5
CG playback | 10
CG editing | 60
Live Recording | 20
Remote control | 20
155